## Info
Informal Test Log
Product: | My Meetings Twin Agent
Platform | Copilto Studio
Product Owner: | Sumit Kaura
Technical Owner: | Dipendra Shekhawat
Ref Defect Log:

## Informal Test Log
S No | FDD | Change request | Environment | Date | Tester | Test Objective | UAT-ID/Scenarios | Result (P/F) | Defect nr | Comment (Optional - eg key parameters, detail of scenario, …)
1 | [5 empty] | Initiate DIA
|  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi |  | No DIA in calendar | P |  | Agent Succefully came back and said no recurring meetings available. No Hallucinations.
2 |  |  | Copilot_Studio_GSC_Dedicated_DEV | 2026-06-23 | Sukant Sondhi |  | 1 Recurring Meeting in calendar | P |  | Successfully retrieved recurring meetings
4 | [5 empty] | Manage DIA
5 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi |  | Yes Configure a new one | P |  | Successfully configured a new one
[5 empty] | Sukant Sondhi |  | No DIA in calendar | P |  | Agent asked to configure one.
6 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi |  | No don't configure a new one | P |  | Went back ot initial topic
7 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi
8 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi
9 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi
10 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi
11 | [5 empty] | My Assigned DIA
12 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi |  | Checking all recurring Meetings | P |  | Gave me 2 Test Meetings (My Agentic Twin Dev & EM Monthly Performance)
13 |  |  |  |  | Sukant Sondhi |  | No DIA Assigned | P |  | No DIA Assigned asking to go back to start.
14 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi |  | Testing My Agentic Twin Dev DIA | P |  | Asked me to select DIAs assigned to this
15 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi |  | Filling out DIAs | P |  | Asked me to fill DIAs manually, auto-fill or select nothing to contribute
16 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi |  | Filling Manually | P |  | Successfully filled Manually
17 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi |  | Auto Fill | P |  | Sucessfully auto filled
18 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Sukant Sondhi |  | Nothing to contribute | P |  | Successfully went back to the initial topic
19 | [5 empty] | Generate Meeting Deck
20 | [5 empty] | Manage DIA
21 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify user can select recurring meetings from calendar where they are organizer | P |  | System displays only recurring meetings where user is organizer and linked to a channel
22 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify user can assign Planner to the meeting | P |  | Planner Plan ID is stored in Dataverse against the meeting
23 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify user can assign KPIs with Owners to the meeting | P |  | KPI-Owner mapping is stored in Dataverse for the meeting
24 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify user can skip KPIs selection | P |  | User can skip KPI selection
25 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify user can assign MS Projects to the meeting | P |  | MS Project mapping is stored against meeting configuration
26 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify user can skip MS PRojects selection | P |  | User can skip MS Project selection
27 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify user can set notification time preferences | P |  | Notification schedule is configured and saved
28 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify user can view list of all configured meeting settings | P |  | System displays all meeting configuration settings
Initiate DIA
31 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify system fetches Red KPIs from PowerBI dataset | P |  | Red KPIs are retrieved and displayed to organizer
32 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify system fetches Amber/Red MS Projects | P |  | Projects with RAG status amber/red are identified
33 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify system fetches overdue Planner tasks | P |  | Overdue tasks from linked Planner are retrieved
34 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify DIA tasks are created for each identified item | P |  | DIA Planner tasks are created with correct owner assignments
35 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify deduplication logic removes duplicate items | P |  | No duplicate DIAs are created for same item from multiple sources
36 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify system identifies all meeting attendees | P |  | All mandatory and optional attendees are retrieved
37 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify DIA task is created for each attendee | P |  | Each attendee receives a DIA task in Planner
38 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify attendees are notified of assigned DIA | P |  | Planner notification is sent to attendees
My Assigned DIA
38 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify agent lists pending DIAs for user | P |  | User sees all assigned DIAs with due dates
39 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify agent drafts DIA based on backend data | P |  | Agent provides pre-populated DIA draft from MS Project data
40 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify user can manually fill DIA form | P |  | User can input all DIA fields manually
41 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify DIA submission stores data in Dataverse | P |  | Completed DIA is saved to Dataverse
42 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify Planner task is marked complete on DIA submission | P |  | Corresponding Planner task status changes to Completed
Generate Meeting Deck
42 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify system retrieves meeting transcript | P |  | Transcript file is fetched from Teams/SharePoint
43 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify system generates meeting summary | P |  | AI generates summary with key points from transcript
44 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify meeting notes are sent to attendees | P |  | Email with notes/summary is delivered to all attendees
46 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify actions/tasks are extracted from transcript | P |  | Follow-up tasks with owners are identified
47 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify system identifies if follow-up meeting is needed | P |  | Agent determines meeting necessity and suggests creation
48 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify Planner tasks are created from transcript actions | P |  | Tasks are created in linked Planner with assignments
48 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify follow-up meeting is create from transcript analysis | P |  | Follow-up meeting is created and invite is sent to necessary attendees
49 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify system aggregates all submitted DIAs for meeting | P |  | All completed DIAs are retrieved for the meeting event
50 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify agenda is generated with time slots | P |  | Agenda calculates time per DIA item
51 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify DIA content is formatted for slides | P |  | DIA insights are converted to HTML/PPT format
52 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify awareness slides are appended to deck | P |  | DIA slides are added to meeting presentation
53 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify final meeting pack is sent to organizer and attendees | P |  | Organizer and attendees receive complete agenda and deck
45 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify slide deck is store in the team Sharepoint location | P |  | Deck file is successfully saved
Data Connectors & Attendee Sync
53 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify PowerBI connector retrieves KPI data | P |  | KPI actual vs target values are fetched
54 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify PowerBI connector retrieves MS Project data | P |  | MSProject actual vs target values are fetched
55 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify Teams/Planner data is accessible | P |  | Team, Channel, and Planner info is retrievable
56 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify required attendees are identified from ownership | P |  | Owners of Red KPIs/Projects are flagged as mandatory
57 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify missing attendees are detected | P |  | System identifies if required owner is not on invite
58 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify meeting invite is updated with required attendees | P |  | New attendees are added as mandatory/optional
59 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify attendance explanation message is generated | P |  | AI generates reason why user is invited
Automation & Sync
59 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify scheduled trigger fires at configured time | P |  | Power Automate flow triggers on schedule
60 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify system checks for stored user meeting configuration | P |  | Existing meeting configs are loaded
61 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify DIA process initiates automatically | P |  | KPI/Project fetch begins without manual intervention
62 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify DIA completion updates Planner task | P |  | One-way sync from Dataverse to Planner works
63 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify error handling logs failures | F |  | Failed sync operations are logged
64 |  |  | Copilot_Studio_GSC_Dedicated_DEV |  | Vitor Antonio |  | Verify DIA-to-Task linkage is maintained | F |  | Dataverse stores Task ID mapping